# Parastatal X – Exploratory Data Analysis Report

FY2023/2024 to FY2025/2026 | Cut-off: 31 May 2026 | Synthetic Data

# 1. Dataset Overview

| Dataset | Volume | Coverage | Key Finding |
| --- | --- | --- | --- |
| Approved Annual Budget | 96 rows | 3 FYs × 32 cost centres | KSh 4,650,000,000 total across 3 FYs |
| Monthly Budget Allocation | 1,152 rows | 3 FYs × 32 CCs × 12 months | Reconciles to annual approved budget |
| Supplementary Budget | 209 rows | 60-90 per FY | Mix of increases (65%) and reductions (35%) |
| Budget Reallocations | 224 rows | 60-100 per FY | 75% approved; 25% pending/rejected |
| Expenditure Transactions | 12,100 rows | ~4,033 per FY on average | KSh 4,134,987,100 total across 3 FYs |
| Commitments | 1,350 rows | ~450 per FY | Open commitments: KSh 700M (FY25/26) |
| Budget Review Requests | 1,000 rows | ~333 per FY | 1,000 requests; significant backlog identified |
| Procurement Plan | 390 rows | ~130 per FY | 12 contracts delayed >45 days |
| Pending Bills | 520 rows | ~173 per FY | KSh 1,121,712,000 outstanding (FY25/26) |
| Revenue and AIA | 1,140 rows | ~380 per FY | KSh 979,529,000 actual vs KSh 1,110,412,000 budget |
| Performance Indicators | 165 rows | 15 indicators × 3 FYs × 3-4 qtrs | Average achievement: ~88% |
| Audit Control Exceptions | 300 rows | ~100 per FY | ~35% resolved; 20% repeat findings |
| Data Quality Log | 250 rows | Across all datasets | ~65% resolved; 18 Critical issues |

# 2. Key Positive Findings

✓ Budget reconciliation accuracy

All monthly allocations reconcile exactly to approved annual budgets across all 3 financial years. Zero reconciliation difference. Demonstrates strong budget management discipline.

✓ FY2025/2026 expenditure growth

YTD expenditure of KSh 1,478,365,800 represents 10.3% year-on-year growth from FY2024/2025 (KSh 1,338,255,800). This is consistent with the budget growth trajectory and organisational expansion.

✓ Revenue stream diversification

Eight revenue streams are active across all 8 regions. Service Fees and Licensing Fees together account for ~58% of actual revenue collections, providing a diversified revenue base.

✓ Commitment payment discipline

The majority of commitments (>75%) are within normal payment timelines. The commitment register is actively maintained with clear status tracking.

✓ High-performing directorates

Finance and Accounts, ICT, and HR Directorates consistently achieve >90% absorption, demonstrating strong budget execution in headquarters functions.

# 3. Key Financial Risks Identified

| Risk | Amount | Level | Root Cause |
| --- | --- | --- | --- |
| Over-expenditure forecast | KSh 63,490,330 | High | Projects & Infrastructure absorbing too fast in some lines while others lag |
| Open commitment exposure | KSh 700,000,000 | High | Procurement-heavy directorates; year-end payment pressure |
| Revenue underperformance | KSh -130,883,000 | Medium | Training and consultancy income below target |
| Pending bills backlog | KSh 1,121,712,000 | High | Documentation and budget insufficiency are top reasons |
| Unprocessed AIE requests | KSh 2,477,786,000 | High | Processing bottleneck at budget office level |

# 4. Absorption Analysis by Directorate

| Directorate | Absorption % | RAG | Comment |
| --- | --- | --- | --- |
| DIR-02 Finance and Accounts | 92.1% | Green | On track |
| DIR-04 Human Resource | 91.5% | Green | On track |
| DIR-06 ICT | 93.8% | Green | Slight over-absorption risk |
| DIR-03 Strategy and Planning | 85.2% | Amber | Monitor closely |
| DIR-09 Communications | 83.7% | Amber | Delayed stakeholder events |
| DIR-12 Projects and Infrastructure | 74.1% | Red | Procurement delays |
| DIR-13 Regional Operations | 71.3% | Red | Activity implementation delays |
| DIR-10 Research and M&E | 68.9% | Red | Research contracts not yet awarded |
| DIR-11 Technical Operations | 70.2% | Red | Equipment procurement delays |
| DIR-05 Procurement | 79.8% | Amber | Good but under expected |

# 5. Data Quality Summary

| Issue Type | Count | Severity | Resolution |
| --- | --- | --- | --- |
| Missing Cost Centre Code | 19 | High | All resolved — mapped to default CC |
| Duplicate Transaction Reference | 14 | Critical | Deduplicated; 14 duplicates removed |
| Incorrect Vote Code | 23 | High | Corrected to valid vote codes |
| Processed Amount > Approved | 8 | Critical | Capped at approved amount |
| Invalid Date | 11 | High | Corrected transposition errors |
| Inconsistent Region Names | 31 | Medium | Standardised to region codes |
| Blank Approval Fields | 27 | Medium | Populated from workflow records |
| Negative Expenditure Amounts | 6 | Critical | Sign corrected |
| Leading/Trailing Spaces | 45 | Low | Trimmed in Power Query |
| Different Capitalisation | 38 | Low | Standardised to uppercase codes |

Data quality score: 96.2% (250 issues in 9,500+ records = 2.6% error rate). This is within the acceptable 2-5% threshold for raw data demonstration. All issues are logged in Data_Quality_Log.csv and a cleaned version is available.