## Risk_Register
RiskID | Category | RiskDescription | Likelihood | Impact | RiskRating | AmountAtRisk | RootCause | ControlMeasures | ResidualRisk | ResponsibleRole | ReviewDate | Status | Comments
RSK-001 | Budget Overrun | Forecast over-expenditure of KSh 63.5M against approved budget | High | High | Critical | 63,490,330 | Higher than expected Q4 expenditure; year-end commitment liquidation pressure | Vote line expenditure controls; reallocation from underspent votes; supplementary budget request | High | Director, Finance and Accounts | 2026-06-10 | Open | CEO directive issued; monitoring weekly
RSK-002 | Commitment Crystallisation | KSh 700M open commitments may crystallise before year-end creating over-expenditure | High | High | Critical | 700,000,000 | Large procurement contracts; delayed delivery; year-end payment timing uncertainty | Commitment review; cancellation of stale orders; phased payment scheduling | High | Director, Supply Chain Management | 2026-06-10 | Open | Individual review of all commitments >KSh 5M initiated
RSK-003 | Revenue Underperformance | Revenue KSh 130.9M below target; AIA funding shortfall | Medium | High | High | 130,883,000 | Lower than expected service demand; delayed licencing renewals; collection inefficiencies | Revenue drive; demand notices; regional collection monitoring | Medium | Revenue Manager | 2026-06-15 | Open | June revenue drive approved by management
RSK-004 | Pending Bills Accumulation | Uncleared invoices totalling KSh 1.1B creating supplier and audit risk | High | Medium | High | 1,121,712,000 | Incomplete documentation; budget insufficiency; approval delays | Priority payment schedule; documentation drive; vote line controls | Medium | Chief Accountant | 2026-06-15 | In Progress | Payment schedule approved; 23 invoices queued
RSK-005 | Procurement Delays | 12 contracts delayed >45 days; risk of undelivered activities | Medium | Medium | High | 150,000,000 | Delayed tender processes; slow supplier mobilisation; specification changes | Contract extensions; re-procurement; performance bond activation | Medium | Director, Supply Chain Management | 2026-06-20 | Open | Contract review meeting 15 June 2026
RSK-006 | Audit Exceptions | 300 audit exceptions; 20% repeat findings; KSh 45M amount at risk | Medium | High | High | 45,000,000 | Missing documents; incorrect coding; segregation of duties gaps | Document drive; training; supervisory reviews; corrective action plans | Medium | Head of Internal Audit | 2026-06-20 | In Progress | Circular issued; 35% documents received
RSK-007 | Low Performance Absorption | 23 cost centres at <80% absorption vs time elapsed | High | Medium | High | 221,634,200 | Activity implementation delays; procurement bottlenecks; staff capacity | Revised work plans; accelerated procurement; management oversight | Medium | Chief Executive Officer | 2026-06-15 | In Progress | CEO directive; bi-weekly reporting started
RSK-008 | Donor Programme Risk | Donor fund underutilisation may trigger clawback or programme disruption | Low | High | Medium | 80,000,000 | Implementation delays; procurement non-compliance; reporting gaps | Revised implementation plan; donor engagement; compliance review | Low | Project Manager | 2026-06-20 | Open | Donor notified; revised plan under preparation
RSK-009 | Data Quality Risk | 2.6% data error rate; 35 critical/high exceptions unresolved | Low | Medium | Medium | 25,000,000 | Data entry errors; system integration gaps; inadequate validation | Data quality log monitoring; Power Query validation; staff training | Low | Data Officer | 2026-06-15 | In Progress | 14 of 35 exceptions resolved
RSK-010 | Unprocessed AIE Backlog | KSh 2.48B in unprocessed approved requests blocking expenditure | High | Medium | High | 2,477,786,000 | Processing capacity constraints; documentation gaps; staff workload | Additional processing staff; 5-day SLA; escalation protocol | Medium | Head of Budget | 2026-06-20 | In Progress | 2 additional finance officers deployed