## Action_Plan
ActionID | Finding | RiskLevel | RecommendedAction | ResponsibleRole | Priority | StartDate | TargetDate | ExpectedFinancialImpact | ExpectedOperationalImpact | Status | ProgressPct | FollowUpDate | Comments
ACT-001 | Forecast over-expenditure of KSh 63.5M across 5 vote lines | High | Impose immediate expenditure controls on at-risk vote lines; reallocate from underspent votes; seek supplementary budget if needed | Director, Finance and Accounts | High | 2026-06-05 | 2026-06-25 | Prevent KSh 63.5M over-expenditure | Maintain fiscal discipline; avoid audit queries | In Progress | 40% | 2026-06-15 | Vote line controls implemented for 3 lines; reallocation request submitted
ACT-002 | KSh 700M open commitments — over-expenditure risk | High | Review all open commitments individually; clear overdue ones before year-end; cancel where goods/services not received | Director, Supply Chain Management | High | 2026-06-05 | 2026-06-25 | Reduce commitment exposure by KSh 200M | Clean procurement register for new FY | In Progress | 30% | 2026-06-12 | 8 commitments escalated to Director level; 3 cancelled
ACT-003 | Revenue 11.8% below target (KSh -130.9M) | Medium | Implement June 2026 revenue drive; issue demand notices; deploy regional revenue teams | Revenue Manager | Medium | 2026-06-05 | 2026-06-30 | Recover KSh 60-80M in June | Improve revenue achievement to 94%+ | Pending | 0% | 2026-06-15 | Revenue drive plan submitted to CEO for approval
ACT-004 | 23 cost centres with Red RAG absorption status | Critical | Weekly reporting to CEO; revised work plans; accelerate pending procurements | Chief Executive Officer | Critical | 2026-06-03 | 2026-06-30 | Improve absorption from 87% to 95%+ | Deliver planned activities and outputs | In Progress | 15% | 2026-06-10 | CEO directive issued; bi-weekly reporting started
ACT-005 | Pending bills >90 days — audit risk | High | Prepare payment schedule; prioritise clearance of all bills >90 days before year-end | Chief Accountant | High | 2026-06-05 | 2026-06-30 | Clear bills outstanding >90 days | Reduce audit queries on pending payments | In Progress | 50% | 2026-06-10 | Payment schedule approved; 23 invoices queued for payment
ACT-006 | Budget review request backlog (KSh 2.48B unprocessed) | High | Deploy additional processing staff; implement 5-day turnaround target; escalate stale requests | Head of Budget | High | 2026-06-05 | 2026-06-20 | Clear KSh 500M backlog by 20 June | Unblock cost centres from executing activities | In Progress | 35% | 2026-06-10 | 2 additional finance officers deployed to budget unit
ACT-007 | 12 procurement contracts delayed | Medium | Issue contract extensions; re-procure where necessary; report to Board on impact | Director, Supply Chain Management | Medium | 2026-06-08 | 2026-06-30 | Recover KSh 150M in payments by year-end | Complete contracted activities before FY close | Pending | 0% | 2026-06-15 | Contract review meeting scheduled for 15 June 2026
ACT-008 | Audit exceptions — missing documents | Medium | Circular to all cost centres; 72-hour deadline for document submission; follow up with Internal Audit | Head of Internal Audit | Medium | 2026-06-05 | 2026-06-20 | Reduce audit exceptions by 60% | Improve audit readiness score | Pending | 10% | 2026-06-12 | Circular issued; 35% of documents received to date
ACT-009 | Donor programme underspend | High | Accelerate donor activities; engage donor on utilisation timeline; submit revised implementation plan | Project Manager | High | 2026-06-05 | 2026-06-30 | Increase donor utilisation by KSh 80M | Maintain donor confidence and programme continuity | Pending | 0% | 2026-06-15 | Donor notified; revised plan under preparation
ACT-010 | Data quality exceptions — 35 unresolved critical/high | Medium | Data Officer to resolve all critical exceptions within 5 days; update DQ log | Data Officer | Medium | 2026-06-05 | 2026-06-15 | Achieve 98%+ DQ score | Improve data reliability for year-end reporting | In Progress | 40% | 2026-06-10 | 14 of 35 exceptions resolved; on track